## FORMS
ACES OF GRACE FORMS MODULE
# | TASK DETAILS | MODULE PARTS | PROGRESS | STATUS | DATE START | DATE ACCOMPLISH | PROCESS | Remarks
1 | Display Top Performing Branch Sales | Home Page | 100% | COMPLETED | 12.15.2018 | 12.15.2018 | • User have option to select date / weekly or monthly • User have also option to select top N • STORED PROCEDURE (spGET_TOP_BRANCH_SALES) | Only For inquiry.
2 | Display Branch in critical stock | Home Page | 0% | ON PROCESS | 12.17.2018
3 | Adding Minimum Stock Level Entry | Branch Stock Inventory | 100% | COMPLETED | 12.17.2018 | 12.17.2018 | • User will update every item on branch inventory the stock warning level • STORED PROCEDURE (Transaction.spUPDATE_BRANCH_STOCK_MIN_LEVEL)
4 | Change Pricing Scheme | Partner Price Setup | 100% | COMPLETED | 1.7.2019 | 1.7.2019 | • Price setup will be base on Partner (Not Applicable Make it only as default price) | • Created new Table (Util.Partner_Price_RF) • SP [UTIL].[spGET_PARTNER_PRICE] • SP [UTIL].[spUPDATE_PARTNER_PRICE]
5 | Change Pricing Scheme Per Branch | Branch Price Setup | 100% | COMPLETED | 1.7.2019 | 1.7.2019 | • Price setup will be base on Branch | • Created new Table (Util.Branch_Price_RF) • SP [UTIL].[spGET_Branch_PRICE] • SP [UTIL].[spUPDATE_BRANCH_PRICE] • Update [MASTER].[INSERT_UPDATE_ITEM] • Update [MASTER].[spINSERT_BRANCH]
STATUS
ON PROCESS
NOT YET STARED
PENDING
COMPLETED
18
19
20
21
22
23
24
25
26
27
28
29
30

## REPORTS
ACES OF GRACE REPORT MODULE
# | TASK DETAILS | MODULE PARTS | PROGRESS | STATUS | DATE START | DATE ACCOMPLISH | PROCESS | Remarks
1 | Summary Display Daily Report / Weekly / Monthly / Yearly of Delivery | Delivery Summary | 100% | COMPLETED | 12.14.2018 | 12.15.2018 | • Subscribe on (View) Transaction.VR_DELIVERY_SUMMARY_TF • Parameter with Two Date (Start and End Date) | This will display summarize total of each Branch
2 | Branch Delivery Summary Per Day/Week/Month/Yearly | Branch Delivery Summary | 100% | COMPLETED | 12.14.2018 | 12.15.2018 | • Subscribe on (View) Transaction.VR_DELIVERY_SUMMARY_TF • Parameter with Two Date (Start and End Date) and BranchCode | This will display specific branch delivery summary per date base on Date Range Input
3 | Selection of Delivery Summary | Delivery Report Module | 100% | COMPLETED | 12.14.2018 | 12.15.2018 | • User need to select date Range and optional selection of Branch.
4 | Display Summary of Sales : Daily / Weekly / Monthly and Yearly | Sales Summary | 100% | COMPLETED | 12.17.2018 | 12.17.2018 | • Subscribe on (View) Transaction.VR_SALES_SUMMARY_TF • Parameter with Two Date (Start and End Date) | This will display summarize total of each Branch
5 | Display Branch Summary of Sales : Daily / Weekly / Monthly and Yearly | Branch Sales Summary | 100% | COMPLETED | 12.17.2018 | 12.17.2018 | • Subscribe on (View) Transaction.VR_SALES_SUMMARY_TF • Parameter with Two Date (Start and End Date) and BranchCode | This will display specific branch sales summary per date base on Date Range Input
6 | Selection of Sales Summary | Sales Report Module | 100% | COMPLETED | 12.14.2018 | 12.15.2018 | • User need to select date Range and optional selection of Branch.
STATUS
ON PROCESS
NOT YET STARED
PENDING
COMPLETED
18
19
20
21
22
23
24
25
26
27
28
29
30